Week 3 Project plan

Phase 1 (Messaging, Participation, Statistics, Quizzes and JavaFX foundation)

Goal

Direct messaging with exclusion enforcement works, participation scores update automatically, warnings and blacklisting are automated, students can attempt quizzes and receive instant results, and the JavaFX desktop application authenticates and detects online/offline state.

| Group Member | Tasks and sub-tasks | Deliverables | Dependencies | Due date |
| --- | --- | --- | --- | --- |
| Justine | - Direct message endpoint: send a message from one user to another with optional exclusion list submitted at the same time - Direct message endpoint: view inbox; list all messages received by the logged-in user, excluding messages where they are in the exclusion list - Direct message endpoint: view sent messages - Participation marks auto-calculation — trigger a score update every time a user creates a post, using a formula based on post count per user per group - Statistics query: post frequency per user per group — used by the lecturer to view engagement - Statistics query: group activity summary — total posts, total topics, most active members Statistics endpoint: expose statistics data as a JSON response for Jonathan's frontend views | Direct messaging with exclusion enforcement working. Participation scores update automatically on post creation. Statistics endpoint returning real data. | Noerine’s messages and participation_marks migrations from week 2. | 11th July at noon |
| Joel (Moderation, Warnings and notifications) | - Warning endpoint: issue a warning to a user with a reason (Admin only) - Warning endpoint: list all warnings for a specific user - Auto-blacklist logic: after a user accumulates two warnings, automatically update their status to Blacklisted and create a blacklist record - Restriction enforcement: blacklisted users are blocked from creating topics, posts, or sending messages - Notification: trigger an in-app notification when a new topic is created in a group the user belongs to - Notification: trigger an in-app notification when a quiz is published for the user's category Notification: trigger an in-app notification when a warning is issued to a user | Warning and blacklist flow working end to end. Auto-blacklist triggers after two warnings. Notifications delivered for key events. | Pearl’s warnings and blacklist migrations from Week 2. | 11th July At noon |
| Noerine (JavaFX Desktop Application (Foundation) | - Set up JavaFX project structure in the team repository under a separate desktop/ directory - Build Login screen in JavaFX — email and password fields, login button, error label - Connect login screen to Laravel Sanctum login endpoint — store the returned token locally for subsequent requests - Build Dashboard screen in JavaFX — navigation buttons for Groups, Topics, Chat, Quiz - Set up local SQLite database inside the JavaFX application for offline caching Implement network state detection — check if the Laravel API is reachable on startup and toggle between online and offline mode | JavaFX application launches, authenticates against the real Laravel API, stores token, and detects online/offline state. | Auth endpoints from Week 1. Laravel API must be stable. | 11th July At noon |
| Pearl (Quiz Attempts, Auto-Marking and results) | - Quiz attempt endpoint: start an attempt — record the student, quiz, and start time - Quiz attempt endpoint: submit a single answer during an attempt - Quiz attempt endpoint: submit the full attempt — trigger auto-marking immediately on submission - Auto-marking logic: compare each submitted answer against the correct_answer field in quiz_questions, sum the marks awarded for correct answers, store total score on the attempt record - Auto-submit logic: if the quiz duration has elapsed and the student has not submitted, automatically submit whatever answers have been recorded so far and mark auto_submitted as true - Quiz results endpoint: return the attempt score, grade, and per-question feedback to the student Quiz results endpoint: return all attempt scores for a specific quiz to the Lecturer | Students can attempt quizzes, auto-submit fires when time expires, marking is automatic, results visible to both student and lecturer. | Access Control middleware. | 11th July at noon |
| Jonathan (Frontend; Quiz, Stats and Admin views) | - Quiz configuration Blade view — form for Lecturers to create a quiz with title, duration, target category, publish date, and questions - Quiz taking Blade view — display questions one at a time with radio button answer options and a countdown timer - Quiz results Blade view — display score, grade, and per-question feedback after submission - Participation statistics Blade view — table showing post count and participation score per user, filterable by group - Administration dashboard Blade view — user list with warning and blacklist action buttons - Recommendation screen Blade view — list of suggested topics (wire to Pearl's endpoint in Week 4) Real-time chat Blade view — message thread display with message input field and send button (Talk to JP about this) | Quiz taking flow works end to end in the browser. Admin dashboard displays users and allows warnings. Statistics screen shows real participation data. | Pearl's quiz endpoints. Justine's statistics endpoint. Joel's warning endpoints. | 11th July, 2026 at noon |

Phase 2 (Recommendations, Portable Document Format Export, JavaFX completion and final polish.)

Goal

Every feature in the SDD is implemented, all fourteen screens work for all three user roles, the JavaFX desktop application syncs offline drafts, and the system is ready for presentation.

| Group Member | Tasks and sub-tasks | Deliverable | Dependencies | Due date |
| --- | --- | --- | --- | --- |
| Pearl (Portable Document Format Export and Database Finalization) | - Install Laravel DomPDF package using Composer: composer require barryvdh/laravel-dompdf - Create a Blade template specifically for Portable Document Format rendering — styled topic thread with all posts and replies - Portable Document Format export endpoint: accept a topic identifier, render the thread as a Portable Document Format, and return it as a downloadable file response - Wire the export button on Jonathan's topic detail view to the endpoint - Final database review: confirm all foreign keys, indexes, and default values match the Software Design Document data dictionary exactly Performance check: add database indexes on frequently queried columns such as group_id on topics and topic_id on posts | Users can export any topic thread as a Portable Document Format. Database fully matches Software Design Document specification. | Jonathan's topic detail Blade view. | 14th July, 2026 |
| Justine (Security Review, Social Sharing and integration Testing) | - Social sharing: generate a publicly accessible shareable Uniform Resource Locator for any topic or post - Social sharing endpoint: accept a topic or post identifier and return a shareable link that opens the topic detail view when visited - Wire social sharing button into Jonathan's topic detail Blade view - Full security review: confirm all routes are protected by the correct Role-Based Access Control middleware — no Student can access Admin endpoints, no unauthenticated request reaches protected routes - Edge case testing: attempt to join a group twice, submit a quiz after time expires, post as a blacklisted user — confirm all edge cases are handled gracefully Integration testing: run through the complete user journey for each role — Student, Lecturer, Admin — from registration to every feature | Social sharing working. All routes protected correctly. No edge cases crash the system. Full role-based user journey confirmed working. | All endpoints from Weeks 2 and 3 must be stable. | 14th July, 2026 |
| Noerine (JavaFX; Offline Sync and Discussion Features) | - JavaFX Group list screen — fetch and display groups from the Laravel API, cache results in local SQLite for offline access - JavaFX Topic list screen — fetch and display topics for a selected group, cache locally - JavaFX Topic detail screen — display posts and replies, allow drafting a reply offline and storing it in local SQLite - Offline sync: when internet connectivity is restored, read all locally cached drafts from SQLite and send them to the Laravel API in a batch request - Conflict handling: if a locally cached draft fails to sync, mark it as failed and notify the user without losing the content JavaFX quiz taking screen — fetch quiz questions from the Application Programming Interface, display with a countdown timer, submit answers on completion | JavaFX application supports offline discussion drafting and syncs to the Laravel Application Programming Interface when reconnected. Quiz taking works in the desktop app. | All Laravel Application Programming Interface endpoints stable. Noerine's Week 3 JavaFX foundation. | 17th July |
| Jonathan (Recommendations, Topic Classification and JavaFX Completion) | - Recommendation engine: query topics from groups the logged-in user belongs to, ordered by most recent post activity — return top ten as personalized suggestions - Trending topics query: identify topics with the highest number of posts in the last seven days across the entire platform - Topic classification: on topic creation, scan the title and category field for predefined keywords and automatically assign a category tag such as Mathematics, Programming, Science, or General - Recommendation endpoint: return personalized suggestions and trending topics as a combined JSON response - Wire recommendation endpoint to Jonathan's recommendation Blade view - JavaFX recommendation screen — display suggested topics fetched from the recommendation endpoint Final JavaFX polish — consistent styling across all screens, loading indicators, error messages for failed Application Programming Interface calls | Recommendations return real, relevant topics. Topic classification assigns categories automatically on creation. JavaFX recommendation screen working. | Post and topic data from Weeks 2 and 3. Jonathan's recommendation Blade view. | 20th July 2026 |
| Joel (Frontend Polish, PDF and final integration) | - Wire Portable Document Format export button on topic detail view to Justine's export endpoint - Wire social sharing button on topic detail view to Joel's sharing endpoint - Wire recommendation screen to Jonathan's recommendation endpoint - Registration Blade view; name, email, password fields with Accept Rules checkbox - Login Blade view email and password fields with error label - Welcome screen Blade view; system title, View Rules button, Login and Register buttons - Full frontend consistency review, confirm navigation works correctly across all 14 screens, no broken links, no missing error messages Responsive layout check; confirm all screens are usable at standard browser widths | All 14 screens from Software Design Document section 6.2 exist, are wired to real endpoints, and work correctly for all three user roles. | All endpoints from Weeks 2, 3, and 4 must be complete. | 22nd July 2026 |